## Estimate
Sl. No | Resource Level | Resource Count | # of Hours | # of Hours
1 | .Net Developer | 1 | 264 | 264
2 | DB Developer | 1 | 264 | 264
3 | Test Engineer | 1 | 128 | 128
4 | Project Manager | 1 | 65.6 | 65.6
Total |  |  |  | 721.6
Project Manager | Product Owner | 22ndMarch | 1
|  | 5th April | 1
|  | 19th April | 1
|  | 30th April | 1
| Scrum Master | All day | 33
37

## Sprint Schedule
Kick off Week
Schedule | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8
Date | 15th March |  |  |  |  | 22nd March |  |  |  |  | 29th March |  |  |  |  | 5th April |  |  |  |  | 12th April |  |  |  |  | 19th April |  |  |  |  | 26th April |  |  |  |  | 3rd May
Day | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Sprint 0 |  |  |  | 1 | 2
Sprint 1 | [5 empty] | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | [25 empty] | Days | Per Day(Hrs) | Total Hrs
Sprint 2 | [15 empty] | 12 | 13 | 14 | 15 | 16 | 17 |  | 18 | 19 | 20 | [15 empty] | 33 | 8 | 264
Sprint 3 | [25 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Note on P9: Author: Holi 29th March
Note on AC10: Author: Ugadi 13th April

## Sprint Meetings
Kick off Week
Schedule | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8
Date | 15th March |  |  |  |  | 22nd March |  |  |  |  | 29th March |  |  |  |  | 5th April |  |  |  |  | 12th April |  |  |  |  | 19th April |  |  |  |  | 26th April |  |  |  |  | 3rd May
Day | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Sprint 0 | KO | DS | DS |  | DS
Sprint 1 | [5 empty] | DS | DS | DS |  | DS |  | DS | DS | DS | DS | [25 empty] | Days | Per Day (Hrs) | Total (Hrs)
Sprint 2 | [15 empty] | DS | DS | DS |  | DS | DS |  | DS | DS | DS | [15 empty] | 33 | 8 | 264
Sprint 3 | [25 empty] | DS | DS | DS |  | DS | DS | DS | DS | DS | DS | DS | DS | DS
Meetings |  |  |  | SP |  |  |  | SRW | SP | [8 empty] | SRW | SP | [8 empty] | SRW | SP | [7 empty] | SRW | PD
[9 empty] | SRE | [9 empty] | SRE | [9 empty] | SRE | [8 empty] | SRE
|  |  |  | Sprint 0 |  |  |  |  | Sprint 1 | [9 empty] | Sprint 2 | [9 empty] | Sprint 3
Note on O9: Author: Holi 29th March
Note on AB10: Author: Ugadi 13th April

## Sprint Meeting Schedule
Sprint Plaining - Total Meetings involved
Type of Meetings | Duration (Mins) | Expected Dates | Intervals | Persons Involved
Kick Off (KO) | Duration (90) |  | Kick Off Meet | Product Owner, Stakeholder, Development Team , Scrum Master
| 6:00-7:30 pm | 15thMarch
Daily Scrum (DS) | Duration (15) |  | Daily | Development Team , Scrum Master
| 11:00-11:15 am | All Days
Sprint Planing(SP) | Duration (60) |  | Beginning of Each Sprint | Development Team , Scrum Master, Product Owner
| ~11:00 am -12:00 pm | 18th March
25thMarch
8th April
22nd April
Sprint Review(SRW) | Duration (60) |  | Ending of Each Sprint (Defination of Done) (specific issues/challenge ) | Development Team , Scrum Master,Product Owner(optional),& Stakeholder(optional)
| ~5:30 pm - 6:30 pm | 24th March
7th April
21st April
4th May
Sprint Retrospective(SRE) | Duration (60) |  | Crosschecking of what went well, loopholes, further improvement in middle of sprint | Development Team , Scrum Master
| ~10:00 am-11:00 am | 25th March
8th April
22nd April
5th May
Project Delivery(PD) | Duration(60) |  | End of Project/ sprint (Defination of Done) | Scrum Master, Product Owner & Stakeholder
| 6:30 pm -7:30 pm | 5th May

## DoD
Definition Of Done
| User Story | Sprint | Product
Code Checked In | Y | Y | Y
Code Completed | Y | Y | Y
Code Reviewed | Y | Y | Y
Unit Tests Passed | Y | Y | Y
Functional Test Passed | Y | Y | Y
Production Test Completed | Y | Y | Y
Acceptance Test Completed | NA | Y | Y
Product Owner Reviewed | NA | Y | Y
Product Owner Accepted | NA | Y | Y

## Sprint vs Activities
Kick off Week
Schedule | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8
Date | 15th March |  |  |  |  | 22nd March |  |  |  |  | 29th March |  |  |  |  | 5th April |  |  |  |  | 12th April |  |  |  |  | 19th April |  |  |  |  | 26th April |  |  |  |  | 3rd May
Day | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Sprint 0 | KO | DS | DS |  | DS
Sprint 1 | [5 empty] | DS | DS | DS |  | DS |  | DS | DS | DS | DS | [25 empty] | Days | Per Day (Hrs) | Total (Hrs)
Sprint 2 | [15 empty] | DS | DS | DS |  | DS | DS |  | DS | DS | DS | [15 empty] | 33 | 8 | 264
Sprint 3 | [25 empty] | DS | DS | DS |  | DS | DS | DS | DS | DS | DS | DS | DS | DS
Meetings |  |  |  | SP |  |  |  | SRW | SP | [8 empty] | SRW | SP | [8 empty] | SRW | SP | [7 empty] | SRW | PD
[9 empty] | SRE | [9 empty] | SRE | [9 empty] | SRE | [8 empty] | SRE
|  |  |  | 1) Customer Meeting 2) Data Sample Collection 3) Basic Design 4) Architecture Plan 5) Resource Mapping 6) Development Environment Setup 7) Daily Standup |  |  |  |  | 1) Development 2) Database Design 3) Unit Testing 4) Write Test Cases 5) Execute Tests 6) Daily Standup 7) Demo to Product Owner/ Stakeholder | [9 empty] | 1) Development 2) Database Support 3) Unit Testing 4) Write Test Cases 5) Execute Tests 6) Daily Standup 7) Demo to Product Owner/Stakeholder | [9 empty] | 1) Application Setup 2) Release Report 3) Documents Preparation 4) Test Report 5) Daily Standup (if required) 6) Deployment 7) Documents Review 8)Customer Meeting
Note on O9: Author: Holi 29th March
Note on AB10: Author: Ugadi 13th April

## Sprint vs Deliverables
Kick off Week
Schedule | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8
Date | 15th March |  |  |  |  | 22nd March |  |  |  |  | 29th March |  |  |  |  | 5th April |  |  |  |  | 12th April |  |  |  |  | 19th April |  |  |  |  | 26th April |  |  |  |  | 3rd May
Day | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Sprint 0 | KO | DS | DS |  | DS
Sprint 1 | [5 empty] | DS | DS | DS |  | DS |  | DS | DS | DS | DS | [25 empty] | Days | Per Day (Hrs) | Total (Hrs)
Sprint 2 | [15 empty] | DS | DS | DS |  | DS | DS |  | DS | DS | DS | [15 empty] | 33 | 8 | 264
Sprint 3 | [25 empty] | DS | DS | DS |  | DS | DS | DS | DS | DS | DS | DS | DS | DS
Meetings |  |  |  | SP |  |  |  | SRW | SP | [8 empty] | SRW | SP | [8 empty] | SRW | SP | [7 empty] | SRW | PD
[9 empty] | SRE | [9 empty] | SRE | [9 empty] | SRE | [8 empty] | SRE
|  |  |  | 1) Input Data Ready (CSV) 2) Requirements Freezed |  |  |  |  | 1) Data Import 2) Data Validation | [9 empty] | 1) Data Output 2) Data Report | [9 empty] | 1) Data Export 2) Application 3) Test Cases 4) Test Report 5) Deployment Document
Note on O9: Author: Holi 29th March
Note on AB10: Author: Ugadi 13th April

## Resource Map
Kick off Week
Schedule | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8
Date | 15th March |  |  |  |  | 22nd March |  |  |  |  | 29th March |  |  |  |  | 5th April |  |  |  |  | 12th April |  |  |  |  | 19th April |  |  |  |  | 26th April |  |  |  |  | 3rd May
Day | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Sprint 0 | KO | DS | DS |  | DS
Sprint 1 | [5 empty] | DS | DS | DS |  | DS |  | DS | DS | DS | DS | [25 empty] | Days | Per Day (Hrs) | Total (Hrs)
Sprint 2 | [15 empty] | DS | DS | DS |  | DS | DS |  | DS | DS | DS | [15 empty] | 33 | 8 | 264
Sprint 3 | [25 empty] | DS | DS | DS |  | DS | DS | DS | DS | DS | DS | DS | DS | DS
Meetings |  |  |  | SP |  |  |  | SRW | SP | [8 empty] | SRW | SP | [8 empty] | SRW | SP | [7 empty] | SRW | PD
[9 empty] | SRE | [9 empty] | SRE | [9 empty] | SRE | [8 empty] | SRE
|  |  |  | 1) Project Manager 2) Test Engineer 3) .Net Developer 4) Database Developer |  |  |  |  | 1) Project Manager 2) .Net Developer 3) Database Developer 4) Test Engineer | [9 empty] | 1) Project Manager 2) .Net Developer 3) Database Developer 4) Test Engineer | [9 empty] | 1) Project Manager 2) .Net Developer 3) Database Developer 4) Test Engineer
Note on O9: Author: Holi 29th March
Note on AB10: Author: Ugadi 13th April